## Sheet1
level_0 | index | Assignee | end_date | Parent Project | start_date | Status | Title | level_of_effort | stack
7 | 7 | Henry Steele | 2025-07-16 | Next phase of citation loader - develop as universal for all institutions. Course lookup etc | 2025-06-22 | In Progress | Add configurations for course lookup matching | 1 | 0
25 | 25 | Henry Steele | 2025-07-02 | Develop Web Component and Drupal Connection for Self Service Portal, and create more processes, depending on not using Open Workflows if we decide that | 2025-06-25 | Completed | Test authentication via Drupal for p and e processing component | 1 | 1
34 | 34 | Henry Steele | 2025-07-17 | Enable Alma to Receive OASIS courses, with ETS | 2025-07-01 | Completed | confirm ETS can in fact work on this project | 1 | 2
14 | 14 | Henry Steele | 2025-07-15 | RHEL7 —> RHEL 9 | 2025-07-14 | Completed | submit request for libpy-prod server which is new. with Python and PHP. | 1 | 1
15 | 15 | Henry Steele | 2025-07-14 | RHEL7 —> RHEL 9 | 2025-07-14 | Completed | submit request for libpy sandbox server. Python including 3.11 in yum. perhaps as part of this ticket I'm going to repoint VIPs from where they were on the libapps-stage server to this one | 1 | 3
16 | 16 | Henry Steele | 2025-07-14 | RHEL7 —> RHEL 9 | 2025-07-14 | Completed | coordinate whats needed on libpy server with Kate | 1 | 4
33 | 33 | Henry Steele | 2025-07-31 | Enable Alma to Receive OASIS courses, with ETS | 2025-07-16 | Completed | provide requiements to ETS | 1 | 1
3 | 3 | Henry Steele | 2025-08-31 | Learning | 2025-07-18 | Not Started | AI theory | 1 | 0
8 | 8 | Henry Steele | 2025-07-22 | RHEL7 —> RHEL 9 | 2025-07-21 | Completed | request VIPs for libpy-prod server | 1 | 2
11 | 11 | Henry Steele | 2025-07-23 | RHEL7 —> RHEL 9 | 2025-07-23 | Completed | communicate with Kate about new libpy-stage server when server is up and can be tested | 1 | 2
13 | 13 | Henry Steele | 2025-07-23 | RHEL7 —> RHEL 9 | 2025-07-23 | Completed | request new VIP for the Ex Libris Touchnet connector with known date and communication to libraries ahead of time. | 1 | 3
10 | 10 | Henry Steele | 2025-07-23 | RHEL7 —> RHEL 9 | 2025-07-30 | Completed | communicate with Kate about libpy-prod server | 1 | 0 | Issue
9 | 9 | Henry Steele | 2025-07-31 | RHEL7 —> RHEL 9 | 2025-07-31 | Completed | Kate tests Springshare A-Z process on libpy-stage and prod | 1 | 2
32 | 32 | Henry Steele | 2025-08-12 | Enable Alma to Receive OASIS courses, with ETS | 2025-08-01 | Completed | test and answer ETS questions about development | 1 | 1
12 | 12 | Henry Steele | 2025-08-01 | RHEL7 —> RHEL 9 | 2025-08-01 | Not Started | when date for Ex Libris touchnet connection VIP repointing comes test | 1 | 2
1 | 1 | Henry Steele | 2025-09-30 | Learning | 2025-08-20 | In Progress | Flask for canonical practice in self service | 1 | 1
0 | 0 | Henry Steele | 2025-08-31 | Learning | 2025-09-01 | Not Started | Angular for Docline Improve best practices | 1 | 0 | Issue
24 | 24 | Henry Steele | 2025-10-29 | Develop Web Component and Drupal Connection for Self Service Portal, and create more processes, depending on not using Open Workflows if we decide that | 2025-09-17 | Completed | Componentize and test authentication for Barnes and noble | 1 | 0
22 | 22 | Henry Steele | 2025-10-31 | Develop Web Component and Drupal Connection for Self Service Portal, and create more processes, depending on not using Open Workflows if we decide that | 2025-09-29 | Not Started | Work on stability and resources through flask learning. And monitoring | 1 | 2
21 | 21 | Henry Steele | 2025-10-15 | Develop Web Component and Drupal Connection for Self Service Portal, and create more processes, depending on not using Open Workflows if we decide that | 2025-09-30 | Not Started | componentize and test authentication for 541 | 1 | 3
23 | 23 | Henry Steele | 2025-11-14 | Develop Web Component and Drupal Connection for Self Service Portal, and create more processes, depending on not using Open Workflows if we decide that | 2025-10-20 | Not Started | Change layout. (Bentoize?) with kate | 1 | 1
2 | 2 | Henry Steele | 2025-08-31 | Learning | 2025-11-01 | Not Started | Agentic AI? | 1 | 0 | Issue
29 | 29 | Henry Steele | 2025-11-14 | Enable Alma to Receive OASIS courses, with ETS | 2025-11-03 | Not Started | Work with John to implement test in Alma | 1 | 0
31 | 31 | Henry Steele | 2025-11-21 | Enable Alma to Receive OASIS courses, with ETS | 2025-11-10 | Not Started | implement | 1 | 2