## plans_fy25_projects_gantt_02102
Hierarchy | Title | Project | Releases (roll-up) | Releases | Team (roll-up) | Team | Assignee | Reporter | Sprint (roll-up) | Sprint | Target start date | Target end date | Due date (roll-up) | Due date | Estimates (d) (roll-up) | Estimates (d) | Parent | Priority | Labels | Components | Issue key | Issue status | Goal | Goal status | Progress (%) | Progress completed (d) | Progress remaining (d) | Progress (%) issue count (IC) | To do IC | In progress IC | Done IC | Total IC | Start date (roll-up) | Start date
Initiative | Institutional Repository Assessment Project | LTS Group Projects |  |  |  |  | Michael J. Hemment | Michael J. Hemment | [5 empty] | 2024-05-31 |  |  |  | High | FY24, FY25 |  | LGP-1 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2023-10-01
Initiative | Tisch Special Collections pages/features | LTS Group Projects |  |  |  |  | Kate Bronstad | Kate Bronstad |  |  |  | 2024-05-31 | [5 empty] | Lowest / Not Set | FY24, FY25 |  | LGP-414 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Data mgmt team web presence | LTS Group Projects |  |  |  |  | Kate Bronstad | Kate Bronstad | [5 empty] | 2024-08-30 |  |  |  | Medium | FY24, FY25 |  | LGP-534 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-01-01
Initiative | RHEL 7 to 9 Upgrade | LTS Group Projects |  |  |  |  | Heather J Klish | Heather J Klish |  |  | 2024-12-02 | 2025-06-30 |  | 2025-06-30 |  |  |  | Low | FY25 |  | LGP-639 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2025-02-03
Initiative | ILLiad User Interface Updates | LTS Group Projects |  |  |  |  | Heather J Klish | Heather J Klish |  |  | 2024-07-09 | 2024-12-31 |  | 2024-12-31 |  |  |  | Medium | FY25, ILLiad |  | LGP-640 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-07-09
Initiative | OpenAthens Implementation | LTS Group Projects |  |  |  |  | Heather J Klish | Heather J Klish |  |  | 2024-07-01 | 2024-12-31 |  | 2025-02-28 |  |  |  | High | FY25 |  | LGP-650 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-06-24
Initiative | Show Availability of Equipment to Borrow on Library Websites | LTS Group Projects |  |  |  |  | Kate Bronstad | Kate Bronstad |  |  |  | 2024-12-31 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-709 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Libguides improvements + authentication. | LTS Group Projects |  |  |  |  | Kate Bronstad | Kate Bronstad | [9 empty] | Lowest / Not Set | FY25 |  | LGP-710 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Twilio integration with ILLiad | LTS Group Projects |  |  |  |  | Heather J Klish | Heather J Klish |  |  | 2024-10-21 | 2025-04-01 |  | 2024-12-31 |  |  |  | Low | FY25 |  | LGP-761 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-10-01
Initiative | Self-service reporting for Aeon and ILLiad | LTS Group Projects |  |  |  |  | Heather J Klish | Heather J Klish |  |  | 2024-09-01 | 2025-06-30 |  | 2025-06-30 |  |  |  | Medium | FY25 |  | LGP-763 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2025-02-03
Initiative | Investigate Denodo/Tableau integration with Aeon and ILLiad self-service reports | LTS Group Projects |  |  |  |  | Heather J Klish | Heather J Klish | [5 empty] | 2025-06-30 |  |  |  | Medium | FY25 |  | LGP-764 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2025-01-01
Initiative | FY25 JumboSearch (Primo) Feature Assessments and Implementation | LTS Group Projects |  |  |  |  | Heather J Klish | Heather J Klish | [5 empty] | 2025-06-30 |  |  |  | Medium | FY25 |  | LGP-789 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-07-01
Initiative | Alma Letter Rewrite Implementation | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-01-01 | [6 empty] | Lowest / Not Set | FY25 |  | LGP-827 | Completed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-09-08
Initiative | ASPace PUI streamlining | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-04-01 | 2024-09-08 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-828 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Leganto new UI Planning and Coordination | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-04-01 | 2024-08-05 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-830 | Completed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Develop Encoded Archival Description (EAD) for ArchivesSpace | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  |  | 2025-02-03 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-831 | On Hold |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2025-06-28
Initiative | Enable Alma to Receive OASIS courses, with ETS | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-09-15 | 2024-12-31 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-832 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Reserves & Reading List Integrations (rollover and anything else) | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-11-15 | 2025-01-31 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-833 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Reserves Lookup Tool and Citation Loader Customizations (maybe cloud app for Lookup Tool) | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-07-16 | 2024-12-01 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-834 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Version Control Project | LTS Group Projects |  |  |  |  | Heather J Klish | Henry Steele |  |  | 2025-02-01 | 2025-06-30 |  | 2025-06-30 |  |  |  | Low | FY25 |  | LGP-835 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-08-20
Initiative | Open Workflows and Alma AI Tools investigation | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2025-02-02 | 2025-09-01 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-836 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | Ginn overlapping course start end dates | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-09-01 | 2024-12-31 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-837 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | ASpace: build regression testing process in Python Selenium | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-08-27 | 2024-12-31 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-1002 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative | upgrade to ASpace 4.0 | LTS Group Projects |  |  |  |  | Henry Steele | Henry Steele |  |  | 2024-10-16 | 2024-12-31 | [5 empty] | Lowest / Not Set | FY25 |  | LGP-1077 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | Assessment requirements gathering | LTS Group Projects |  |  |  |  | John A Stephenson | John A Stephenson | [9 empty] | Lowest / Not Set | FY25 |  | LGP-1078 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | TUSM profiles project planning | LTS Group Projects |  |  |  |  | John A Stephenson | John A Stephenson | [9 empty] | Lowest / Not Set | FY25 |  | LGP-1079 | In Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | Elements v6.14+ upgrade | LTS Group Projects |  |  |  |  | John A Stephenson | John A Stephenson | [9 empty] | Lowest / Not Set | FY25 |  | LGP-1080 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task | Discovery site redesign | LTS Group Projects |  |  |  |  | John A Stephenson | John A Stephenson | [9 empty] | Lowest / Not Set | FY25 |  | LGP-1081 | Not Started |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0