## Sheet1
Current Status | Priority | task | Sub-Project Name | Project Lead(s) | Request Received Date | Customer | Directorate | Needs Resources Outside of Dept. | Type of Resources Needed | level_of_effort | Directorates Involved | Sub-Directorates Involved | start_date | end_date | Status | Notes | Category | Resource Categorization
Highest | Highest | RHEL 7 to 9 Upgrade |  | Heather Klish, Henry Steele |  |  | Library Technology Services | Y | collaboration with ESCP | 5 | ITEE-ESCP |  | 2024-04-28 | 2024-05-17 | Not started | libapps-prod-01, libapps-stage-01, libarcsdb-dev-03.it, libarcs-dev-04.it, libarcs-prod-02.uit, libpy-stage-01, libarcs-prod-02.it.tufts.edu, libarcs-dev-04.it.tufts.edu, libarcsdb-dev-03.it.tufts.edu | 1. TTS Committed | Adequately Staffed
| Medium | Reserves & Reading List Integrations - Phase II? III? |  | Henry Steele |  |  | Library Technology Services | Y | perhaps work with SIS depending on whether A: retrieving cost is feasible given the methods we have; and B: SIS has time to work on it | 5 | SIS |  | 2024-06-01 | 2024-07-03 | Not started |  | 1. TTS Committed
| Medium | build out and build adoption of reserves lookup tool and citation loader into library reserve desk workflows |  | Henry Steele |  | Library Circ Reserve Desks | Library Technology Services |  |  | 4 | Peter Franey and group working with LLAMA servers |  | 2024-05-10 | 2024-06-15 | In progress | other than implementing and adapting these tools to library reserve desks, the other part of this work is trying to integrate a call to our local LLAMA AI servers via AI so that citations from faculty email can be pasted directly into an input box, and the AI determines what the metadata fields are (TItle, Author, Contributor, Publisher Year) and then submits that the PNX lookup
| Medium | finishing Ruby on Rails course, implement CI/CD especially pushing plugin repos to local ASPace, and flesh and continue to evolve out project management processes |  | Henry Steele |  | internal to dept | Library Technology Services |  |  | 3 |  |  | 2024-06-16 | 2024-07-03
| Medium | rececive OASIS courses in course feed into Alma |  | Henry Steele |  | HHSL and Vet | Library Technology Services | Y, possibly for shibboleth assistance | ETS would need to build this feed, including the rollover feed, based on the extract SIS defined for outputs, but in their system as source | 3 | ETS |  | 2024-06-01 | 2024-07-03 | Not started | hopefully we can also define a rollover feed to meet Vet request
| Medium | Automate Regular Holdings Reports (Springshare, Docline, and Read by QxMD) |  | Henry Steele |  |  | Library Technology Services | N |  | 3 |  |  | 2024-05-18 | 2024-05-31 | In progress | almost done. waiting for QxMD to complete some development needed on their end to receive the files that the publishing profile FTP'ed
| Highest | Alma letter rewrite implementation |  | Henry Steele |  | CRT/libraries | Library Technology Services | N |  | 3 |  |  | 2024-06-27 | 2024-06-27 | In progress | letter rewrite for better customer service and currency. CRT created language for this. LTS will put in place in sandbox, coordinate testing on sandbox, and implement on prod
| Highest | Leganto new UI -- cordinate launch |  | Henry Steele |  | RRLT/libraries | Library Technology Services | N |  | 3 |  |  | 2024-06-04 | 2024-07-03 | In progress | Most of this work is coordinating or even just checking on the communication plan and documentation rewrite that RRLT is doing. And some implementation in July
| Low | Develop Encoded Archival Description (EAD) plugin for ArchivesSpace |  | Henry Steele |  |  | Library Technology Services | N |  | 3 |  |  | 2024-07-04 | 2024-07-16 | Not started | This is medium effort only because I've done some of hte work already for this. Althouhg the priority is low, the positive user impact could be high because they wouldn't have to wait as long as several minutes for the EAD finding aid to generate on the fly in the PUI
| Highest | ASpace PUI streamlining |  | Henry Steele |  | TARC | Library Technology Services | N |  | 5 |  |  | 2024-06-01 | 2024-09-01 | In progress | Because TARC wants this project completed over this summer, I have restricted the deliverable to a working version on the sandbox, because it's impossible to tell if TARC will be done testing it by then.